## Test Plan
Test Plan

## Report
Test Case Report
Project Name : Bikroy.com Mobile App
Module Name : Registration, sign Up and Sign In.
Written By : Nurul Huda Pranto
Executed By : Nurul Huda Pranto
Reviewed By : Ehsanul Alam Sabbir
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| #REF! | #REF! | #REF! | #REF! | #REF!
Grand Total | #REF! | #REF! | #REF! | #REF! | #REF!
LIMITATIONS | [5 empty] | Total No. | Status
[6 empty] | #REF! | PASS
Documents | Received |  |  | Useful |  | #REF! | FAIL
PRD | No |  |  | No |  | #REF! | Not Executed
USER STORY | No |  |  | No |  | #REF! | Out Of Scopre

## Test Case
TEST CASE |  |  | Product Name | Bikroy.com
PASS |  |  | Module Name | Sign up and Sign in
FAIL |  |  | TC Start Date | 2025-07-06
Not Executed |  |  | TC End Date
Out of Scope |  |  | Test Case Developed By | Nurul Huda Pranto
TOTAL |  |  | Test Case Reviewd By | Ehsanul Alam Sabbir
#TestCase ID | Module | Feature | Test Case | Expected Result | Actual Result | Test Data | Test Steps | Bug ScreenShorts | Status
| User Management | UI Testing | Checking spelling or grammtical mistakes | No spelling or grammatical mistakes | Found as per expectation | N/A | 1. Goto the Bikroy app in playstore. |  | Passed
TC001 |  |  | Verify the font, text, color and style | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the Bikroy app. 2. Click on the registration Button. 3. Than check font, text, color and style. |  | Passed
|  |  | Verifying mandatory field is marked with red asterisk | Red asterisk should be present | Found as per expectation | N/A | 1. Goto the Bikroy app 2. Check red asterisk beside mandatory field |  | Passed
TC002
|  |  | Checking the hovering over the fields | A text should appear over the fields | Found as per expectation | N/A | 1. Goto the Aarong app 2. Hover over every filed. |  | Passed
TC003 |  |  | Checking allignment of the fields | Proper alignment of the fields should be present | Found as per expectation | N/A | 1. Goto the Aarong app 2. Click on Registraion button. 3. Check alignment of the field. |  | Passed
|  | Sign Up | Entering blank at first position in firstname and lastname field | Should not accept the provided input | Found as per expectation | Aakk ppjssg | 1. Goto the Aarong app 2. Click on Registraion button. 3. Input blank at first position in firstname and lastname field. |  | Passed
TC004
|  |  | Entering blank at last position in firstname and lastname field | Should not accept the provided input | Found as per expectation | Aakk ppjssg | 1. Goto the Bikroy app 2. Click on Registraion button. 3. Input blank at last position in firstname and lastname field. |  | Passed
TC005 |  |  | Checking alert message for all mandatory fileds | Should pop an error message | Not found as per expection | N/A | 1. Goto the Bikroy app 2. Click on Registraion button. 3. Keeping blank in each field and checking repeatedly |  | Failed
|  |  | Inputing firstname and lastname with special characters | Should not accept the provided input | Not found as per expection | *&&*(){}[] | 1. Goto the Bikroy app 2. Click on Registraion button. 3. Enter special characters in firstname and lastname field |  | Failed
TC006
|  |  | Inputing firstname and lastname with numbers | Should not accept the provided input | Not found as per expection | 123456789 | 1. Goto the Bikroy app 2. Click on Registraion button. 3. Enter special characters in firstname and lastname field |  | Failed
TC007 |  |  | Inputing firstname and lastname with decimal numbers | Should not accept the provided input | Not found as per expection | 12.34.56.78 | 1. Goto the Bikroy app 2. Click on Registraion button. 3. Enter decimal numbers in |  | Failed
|  |  | Inputing firstname and lastname with alphanumeric characters | Should not accept the provided input | Not found as per expection | pranto1234 | 1. Goto the Bikroy app 2. Click on Registraion button. 3. Enter alphanumeric characters in firstname and lastname field |  | Failed
TC008
|  |  | Validating an email id can only be used one time | Should not allow user to register and display a pop message | Found as per expectation | prantoahmed900.com | 1. Goto the Bikroy app 2. Click on Registraion button. 3. Fill the email address with already registered email |  | Passed
TC009 |  |  | Validating an mobile number can only be used one time | Should not allow user to register and display a pop message | Found as per expectation | 123456789 | 1. Goto the Bikroy app 2. Click on Registraion button. 3. Fill the mobile number with already registered email |  | Passed
|  |  | Enter an invalid mobile | Should not accept the provided input | Not found as per expection | 5418814468 | 1. Goto the Bikroy app 2. Click on Registraion button. 3. Enter an invalid mobile number |  | Failed
TC0010
|  |  | Entering blank at position gender | Should not accept the provided input | Not found as per expection | Null |  |  | Failed
TC0011 |  |  | Entering blank at position Date of Birth | Should not accept the provided input | Not found as per expection | Null |  |  | Failed
|  |  | Enter an invalid emaiil address | Should not accept the provided input | Not found as per expectation | Invalid |  |  | Failed
TC0012
|  | Sign In | Keeping email and password field blank | Should not allow user to login and display an error messeage | Found as per expectation | N/A | 1. Goto the Bikroy app 2. Click on login button. 3. Keep both the fields blank |  | Passed
TC0013 |  |  | Checking if the data in password is masked | Should be masked | Found as per expectation | pranto@999 | 1. Goto the Bikroy app 2. Click on login button. 3. Input values in password field and check if it is masked |  | Passed
|  |  | Checking login wrong credentials in email and password field | Should not allow user to login and display an error messeage | Found as per expectation |  | 1. Goto the Bikroy app 2. Click on login button. 3. Input valid credentials in email and password field |  | Passed
TC0014
|  |  | Verifying ‘Forgot Password’ functionality | Should sent an email for recovering password | Found as per expectation |  | 1. Goto the Bikroy app 2. Click on login button. 3. Click on 'Forgot Password 4. Check email |  | Passed
TC0015 |  |  | Enabling the 'Show Password' checkbox of 'Set a New Password' | Password should be dispayed | Found as per expectation |  | 1. Goto the Bikroy app 2. Click on login button. 3.Click on 'Forgot Password' 4. Check the registered email 5. Click on 'Set up a New Password' 6. Enable 'Show Password' checkbox |  | Passed
|  | Improvement Scope | Password must with Characters, number, symbol
A maximum length of the password should be defined
'Remember Me' checkbox should be selected according to user

## Bug Report
Bug Reporting | Bug Reporting | Bug Reporting | Bug Reporting | Bug Reporting | Bug Reporting
# SL 05 | # SL 06 | # SL 07 | # SL 08 | # SL 08 | # SL 08
Issue: Checking alert message for all mandatory fileds | Issue: Inputing firstname and lastname with special characters | Issue: Inputing firstname and lastname with numbers. | Issue: Inputing firstname and lastname with decimal numbers | Issue: Inputing firstname and lastname with alphanumeric characters. | Issue: Inputing firstname and lastname with alphanumeric characters.
Reproducing Steps: | Reproducing Steps: | Reproducing Steps: | Reproducing Steps: | Reproducing Steps: | Reproducing Steps:
1. Goto the Bikroy App | 1. Goto the Bikroy App | 1. Goto the Bikroy App | 1. Goto the Bikroy App | 1. Goto the Bikroy App | 1. Goto the Bikroy App
2. Click on Registration button. | 2. Click on Registration button. | 2. Click on Registration button. | 2. Click on Registration button. | 2. Click on Registration button. | 2. Click on Registration button.
3. Keeping blank in each and checking repeatedly. | 3. Keeping blank in each field and checking. | 3. Enter numbers in firstname and lastname field | 3. Enter numbers in firstname and lastname field | 3. Enter alphanumeric characters in firstname and lastname field. | 3. Enter alphanumeric characters in firstname and lastname field.
Environment: Production | Environment: Production | Environment: Production | Environment: Production | Environment: Production | Environment: Production
Module: Sign Up | Module: Sign Up | Module: Sign Up | Module: Sign Up | Module: Sign Up | Module: Sign Up
Severity: P1 | Severity: P1 | Severity: P1 | Severity: P1 | Severity: P1 | Severity: P1
Screenshot: | Screenshot: | Screenshot: | Screenshot: | Screenshot: | Screenshot:
Responsible QA: Nurul Huda Pranto | Responsible QA: Nurul Huda Pranto | Responsible QA: Nurul Huda Pranto | Responsible QA: Nurul Huda Pranto | Responsible QA: Nurul Huda Pranto | Responsible QA: Nurul Huda Pranto